## Gantt chart
System Name: | Restaurant Management Systems
Members: | Mykel Seth C. Gella |  | A | 42
| Drew Adrien C. Odilao |  | B | 19
| John Wayne M. Largo |  | C | 25
Statuses: |  | Todo
In-Progress
On-hold
Done
[5 empty] | August | [7 empty] | September | [29 empty] | October | [30 empty] | November
Tasks | Assignee | Date Started | Date Finished | Status | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1. LOGIN |  | 2024-08-25 | 2024-10-21 | Done
.1 Login Functionality | C | 2024-08-25 | 2024-08-25 | Done
.2 Login UI | C | 2024-08-25 | 2024-08-25 | Done
.3 Integrating DB | C | 2024-08-25 | 2024-09-02 | Done
.4 Redesign/Polishing | A | 2024-10-21 | 2024-10-21 | Done
2. SIGNIN |  | 2024-08-25 | 2024-10-21 | Done
.1 Signin Functionality | C | 2024-08-25 | 2024-08-25 | Done
.2 Login UI | C | 2024-08-25 | 2024-08-25 | Done
.3 Integrating DB | C | 2024-08-25 | 2024-08-25 | Done
.4 Redesign/Polishing | A | 2024-10-21 | 2024-10-21 | Done
3. LOGOUT |  | 2024-10-24 | 2024-11-02 | Done
.1 Logout Functionality | C | 2024-10-24 | 2024-10-29 | Done
.2 Logout UI | C | 2024-10-24 | 2024-10-29 | Done
.3 Redesign/Polishing | A | 2024-11-01 | 2024-11-02 | Done
4. Password Recoverery/Register |  | 2024-08-25 | 2024-11-02 | Done
.1 Integrating DB | B | 2024-08-25 | 2024-08-29 | Done
.2 UI | B | 2024-08-25 | 2024-09-02 | Done
.3 Functionality | B | 2024-10-13 | 2024-10-13 | Done
.4 Redesign/Polishing | A | 2024-11-01 | 2024-11-02 | Done
5. Payments/Billing | A | 2024-11-16 | 2024-11-18 | Done
6.Dashboard/Reporting | A | 2024-10-21 | 2024-11-01 | Done
7. Food Menu |  | 2024-10-21 | 2024-11-02 | Done
.1 Integrating db and Ui | A | 2024-10-21 | 2024-10-27 | Done
.2 Add (CREATE) | A | 2024-10-21 | 2024-10-27 | Done
.2 DIsplay (READ) | A | 2024-10-21 | 2024-10-27 | Done
.4 Update(UPDATE) | A | 2024-10-28 | 2024-11-04 | Done
.5 Delete (Delete) | A | 2024-10-28 | 2024-11-01 | Done
.6 Relations | A | 2024-11-26 | 2024-11-28 | Done
.7 Redesign/Polishing | A | 2024-11-01 | 2024-11-02 | Done
8. Order Management |  | 2024-10-21 | 2024-11-02 | Done
.1 Integrating db and Ui | B | 2024-10-21 | 2024-10-27 | Done
.2 Add (CREATE) | B | 2024-10-21 | 2024-10-27 | Done
.2 DIsplay (READ) | B | 2024-10-21 | 2024-10-27 | Done
.4 Update(UPDATE) | A | 2024-10-28 | 2024-11-10 | Done
.5 Delete (Delete) | C | 2024-10-28 | 2024-11-01 | Done
.6 Relations | A | 2024-11-10 | 2024-11-16 | Done
.7 Redesign/Polishing | A | 2024-11-01 | 2024-11-02 | Done
9. Reservation Management |  | 2024-10-21 | 2024-11-02 | Done
.1 Integrating db and Ui | B | 2024-10-21 | 2024-10-27 | Done
.2 Add (CREATE) | B | 2024-10-21 | 2024-10-27 | Done
.2 DIsplay (READ) | B | 2024-10-21 | 2024-10-27 | Done
.4 Update(UPDATE) | A | 2024-10-28 | 2024-11-02 | Done
.5 Delete (Delete) | C | 2024-10-28 | 2024-11-01 | Done
.6 Relations | A | 2024-11-05 | 2024-11-08 | Done
.7 Redesign/Polishing | A | 2024-11-01 | 2024-11-02 | Done
10.User Authentication and Access Control | A | 2024-11-24 | 2024-11-26 | Done
11.Order Management |  | 2024-10-21 | 2024-11-02 | Done
.1 Integrating db and Ui | C | 2024-10-21 | 2024-10-27 | Done
.2 Add (CREATE) | B | 2024-10-21 | 2024-10-27 | Done
.2 DIsplay (READ) | B | 2024-10-21 | 2024-10-27 | Done
.4 Update(UPDATE) | A | 2024-10-28 | 2024-10-28 | Done
.5 Delete (Delete) | C | 2024-10-28 | 2024-11-01 | Done
.6 Relations | A | 2024-11-27 | 2024-11-27 | Done
.7 Redesign/Polishing | A | 2024-11-01 | 2024-11-02 | Done
12.Inventory Management |  | 2024-10-21 | 2024-11-02 | Done
.1 Integrating db and Ui | C | 2024-10-21 | 2024-10-27 | Done
.2 Add (CREATE) | B | 2024-10-21 | 2024-10-27 | Done
.2 DIsplay (READ) | B | 2024-10-21 | 2024-10-27 | Done
.4 Update(UPDATE) | A | 2024-10-28 | 2024-11-05 | Done
.5 Delete (Delete) | C | 2024-10-28 | 2024-10-30 | Done
.6 Relations | A | 2024-10-29 | 2024-11-01 | Done
.7 Redesign/Polishing | A | 2024-11-01 | 2024-11-02 | Done
13.Employee Scheduling |  | 2024-10-21 | 2024-11-02 | Done
.1 Integrating db and Ui | C | 2024-10-21 | 2024-10-27 | Done
.2 Add (CREATE) | C | 2024-10-20 | 2024-10-20 | Done
.2 DIsplay (READ) | C | 2024-10-20 | 2024-10-20 | Done
.4 Update(UPDATE) | A | 2024-10-28 | 2024-10-30 | Done
.5 Delete (Delete) | C | 2024-10-28 | 2024-10-29 | Done
.6 Relations | A | 2024-10-30 | 11/1/204 | Done
.7 Redesign/Polishing | A | 2024-11-01 | 2024-11-02 | Done
14.Customer Reservation Management |  | 2024-10-21 | 2024-11-02 | Done
.1 Integrating db and Ui | C | 2024-10-21 | 2024-10-27 | Done
.2 Add (CREATE) | B | 2024-10-21 | 2024-10-27 | Done
.2 DIsplay (READ) | B | 2024-10-21 | 2024-10-27 | Done
.4 Update(UPDATE) | A | 2024-10-28 | 2024-10-28 | Done
.5 Delete (Delete) | C | 2024-10-28 | 2024-11-01 | Done
.6 Relations | A | 2024-10-30 | 2024-11-01 | Done
.7 Redesign/Polishing | A | 2024-11-01 | 2024-11-02 | Done
15.Menu Management |  | 2024-10-21 | 2024-11-02 | Done
.1 Integrating db and Ui | C | 2024-10-21 | 2024-10-27 | Done
.2 Add (CREATE) | B | 2024-10-21 | 2024-10-27 | Done
.2 DIsplay (READ) | B | 2024-10-21 | 2024-10-27 | Done
.4 Update(UPDATE) | A | 2024-10-28 | 2024-10-28 | Done
.5 Delete (Delete) | C | 2024-10-28 | 2024-11-01 | Done
.6 Relations | A | 2024-10-30 | 2024-11-01 | Done
.7 Redesign/Polishing | A | 2024-11-01 | 2024-11-02 | Done
16.Table Management |  | 2024-10-21 | 2024-11-02 | Done
.1 Integrating db and Ui | C | 2024-10-21 | 2024-10-27 | Done
.2 Add (CREATE) | B | 2024-10-21 | 2024-10-27 | Done
.2 DIsplay (READ) | B | 2024-10-21 | 2024-10-27 | Done
.4 Update(UPDATE) | A | 2024-10-28 | 2024-10-28 | Done
.5 Delete (Delete) | C | 2024-10-28 | 2024-11-01 | Done
.6 Relations | A | 2024-10-30 | 2024-11-01 | Done
.7 Redesign/Polishing | A | 2024-11-01 | 2024-11-02 | Done
17.Payment Processing | A | 2024-11-26 | 2024-11-28 | Done
18.Notifications and Alerts | A | 2024-11-09 | 2024-11-11 | Done
19.Role-Based Access Control | A | 2024-11-04 | 2024-11-08 | Done
20.Security and Data Privacy | C | 2024-11-01 | 2024-11-02 | Done
21.Advanced Search Functionality | A | 2024-11-28 | 2024-11-30 | Done

## Gantt Chart-Final (hidden)
System Name | Restaurant Management Systems
Members: | Mykel Seth C. Gella | A
| Drew Adrien C. Odilao | B
| John Wayne M. Largo | C
Statuses |  | Todo
In-Progress
|  | On-hold | On-hold
|  | Done | Done
[5 empty] | August | [7 empty] | September
Tasks | Assignee | Date Started | Date Finished | Status | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 4
1. LOGIN
1.1. Creating UI | C | 2024-08-25 | 2024-08-25 | Done
1.2 Appling Forms/Views | C | 2024-08-25 | 2024-08-25 | Done
1.2. Integrate with DB | C | 2024-08-25 | 2024-09-02 | Done
1.3 Redesign | B | 2024-10-21 | 2024-10-21 | Done
2. SIGNIN
2.1 Creating UI | C | 2024-08-25 | 2024-08-25 | Done
2.2 Applying Functionality | C | 2024-08-25 | 2024-08-25 | Done
2.3 Redesign | B | 2024-10-21 | 2024-10-21 | Done
2.4 Integrate with DB | C | 2024-08-25 | 2024-08-25 | Done
3. LOGOUT
2.1 Creating UI | A | 2024-08-25 | 2024-08-29 | Done
2.1 Integreate with DB | A | 2024-08-25 | 2024-09-02 | Done
4. Password Recoverery/Register
3.1 Creating UI | B | 2024-08-25 | 2024-08-29 | Done
3.2 Integrate with DB | B | 2024-08-25 | 2024-09-02 | Done
3.3 Applying Functionality | B | 2024-10-13 | 2024-10-13 | Done
4. Support/FAQ/FeedBack
4.1 Creating UI | C | 2024-09-02 | 2024-09-06 | Done
4.2 Integrate with DB | C | 2024-09-02 | 2024-09-10 | Done
5. Payments/Billing
5.1 Creating UI | B | 2024-09-02 | 2024-09-08 | Done
5.2 Payment Processing | B | 2024-09-09 |  | Done
6.Dashboard
6.1 Creating UI | A | 2024-10-20 |  | Done
6.2 Implementing Navigation | C | 2024-10-20 |  | Done
6.3 Adding functionality | C | 2024-10-20 |  | Done
6.4 Finalizing |  | 2024-10-20 |  | Done
6. Food Menu
6.1 Creating UI | C |  |  | Done
6.2 Integreate with DB | C |  |  | Done
7. Order Management
7.1 Creating UI | A |  |  | Done
7.2 Integreate with DB | A |  |  | Done
7.3 Order Tracking | A |  |  | Done
7.4 Order Summary |  |  |  | Done
8. Reservation Management
8.1 Creating UI | C |  |  | Done
8.2 Integreate with DB | C |  |  | Done
8.3 Reservation Tracking | C |  |  | Done
8.4 Reservation Creating | C |  |  | Done
9.User Authentication and Access Control | A |  |  | Done
10.Order Management | A |  |  | Done
11.Inventory Management | A |  |  | Done
12.Employee Scheduling | A |  |  | Done
13.Customer Reservation Management | A |  |  | Done
14.Reporting | A |  |  | Done
15.Menu Management | A |  |  | Done
16.Table Management | A |  |  | Done
17.Payment Processing | A |  |  | Done
18.Notifications and Alerts | A |  |  | Done
19.Role-Based Access Control | A |  |  | Done
20.Security and Data Privacy | A |  |  | Done
21.Advanced Search Functionality | A |  |  | Done
22.Feedback and Review Management | A |  |  | Done
23.Password Management | A |  |  | Done

## Sheet1 (hidden)
System Name | Restaurant Management Systems
Members: | Mykel Seth C. Gella | A
| Drew Adrien C. Odilao | B
| John Wayne M. Largo | C
Statuses |  | Todo
In-Progress
|  | On-hold | On-hold
|  | Done | Done
[5 empty] | August | [7 empty] | September
Tasks | Assignee | Date Started | Date Finished | Status | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 4
1. LOGIN
1.1. Creating UI | C | 2024-08-25 | 2024-08-25 | Done
1.2 Appling Forms/Views | C | 2024-08-25 | 2024-08-25 | Done
1.2. Integrate with DB | C | 2024-08-25 | 2024-09-02 | Done
1.3 Redesign | B | 2024-10-21 | 2024-10-21 | Done
2. SIGNIN
2.1 Creating UI | C | 2024-08-25 | 2024-08-25 | Done
2.2 Applying Functionality | C | 2024-08-25 | 2024-08-25 | Done
2.3 Redesign | B | 2024-10-21 | 2024-10-21 | Done
2.4 Integrate with DB | C | 2024-08-25 | 2024-08-25 | Done
3. LOGOUT
2.1 Creating UI | A | 2024-08-25 | 2024-08-29 | Done
2.1 Integreate with DB | A | 2024-08-25 | 2024-09-02 | Done
4. Password Recoverery/Register
3.1 Creating UI | B | 2024-08-25 | 2024-08-29 | Done
3.2 Integrate with DB | B | 2024-08-25 | 2024-09-02 | Done
3.3 Applying Functionality | B | 2024-10-13 | 2024-10-13 | Done
4. Support/FAQ/FeedBack
4.1 Creating UI | C | 2024-09-02 | 2024-09-06 | Done
4.2 Integrate with DB | C | 2024-09-02 | 2024-09-10 | Done
5. Payments/Billing
5.1 Creating UI | B | 2024-09-02 | 2024-09-08 | Done
5.2 Payment Processing | B | 2024-09-09 |  | Done
6.Dashboard
6.1 Creating UI | A | 2024-10-20 |  | Done
6.2 Implementing Navigation | C | 2024-10-20 |  | Done
6.3 Adding functionality | C | 2024-10-20 |  | Done
6.4 Finalizing |  | 2024-10-20 |  | Done
6. Food Menu
6.1 Creating UI | C |  |  | Done
6.2 Integreate with DB | C |  |  | Done
7. Order Management
7.1 Creating UI | A |  |  | Done
7.2 Integreate with DB | A |  |  | Done
7.3 Order Tracking | A |  |  | Done
7.4 Order Summary |  |  |  | Done
8. Reservation Management
8.1 Creating UI | C |  |  | Done
8.2 Integreate with DB | C |  |  | Done
8.3 Reservation Tracking | C |  |  | Done
8.4 Reservation Creating | C |  |  | Done
User Authentication and Access Control | A |  |  | Done
Order Management | A |  |  | Done
Inventory Management | A |  |  | Done
Employee Scheduling | A |  |  | Done
Customer Reservation Management | A |  |  | Done
Reporting | A |  |  | Done
Menu Management | A |  |  | Done
Table Management | A |  |  | Done
Payment Processing | A |  |  | Done
Notifications and Alerts | A |  |  | Done
Role-Based Access Control | A |  |  | Done
Security and Data Privacy | A |  |  | Done
Advanced Search Functionality | A |  |  | Done
Feedback and Review Management | A |  |  | Done
Password Management | A |  |  | Done

## Gantt chart Simplified (hidden)
System Name | Restaurant Management Systems
Members: | Mykel Seth C. Gella | A
| Drew Adrien C. Odilao | B
| John Wayne M. Largo | C
Statuses |  | Todo
In-Progress
|  | On-hold | On-hold
|  | Done | Done
[5 empty] | August | [7 empty] | September | [29 empty] | October | [30 empty] | November
Tasks | Assignee | Date Started | Date Finished | Status | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 6
1. LOGIN | C |  |  | Done
2. SIGNIN | C |  |  | Done
3. LOGOUT | C |  |  | Done
4. Password Recoverery/Register | B |  |  | Done
5. Support/FAQ/FeedBack |  |  |  | Todo
6. Payments/Billing |  |  |  | Todo
7.Dashboard | A |  |  | InProgress
8. Food Menu |  |  |  | InProgress
9. Order Management |  |  |  | InProgress
10. Reservation Management |  |  |  | Todo
11.User Authentication and Access Control |  |  |  | InProgress
12.Order Management |  |  |  | InProgress
13.Inventory Management |  |  |  | InProgress
14.Employee Scheduling |  |  |  | InProgress
15.Customer Reservation Management |  |  |  | InProgress
16.Reporting |  |  |  | Todo
17.Menu Management |  |  |  | Inprogress
18.Table Management |  |  |  | Inprogress
19.Payment Processing |  |  |  | Todo
20.Notifications and Alerts |  |  |  | Todo
21.Role-Based Access Control |  |  |  | Todo
22.Security and Data Privacy | C |  |  | Done
23.Advanced Search Functionality |  |  |  | Todo
24.Feedback and Review Management |  |  |  | Todo
25.Password Management |  |  |  | Todo